## Building
[28 empty] | 2023 |  |  |  |  | 2024
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | ACTUAL DURATION | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
8 | [7 empty] | WBS-1 | 1 | Building Construction | 276 | 276 |  | 2023-09-18 | 2024-10-07 | 2023-09-18 | 2024-09-20 | 2023-09-18 | 2023-10-16 |  |  |  | 0 | 3.163% | 43000 | 41400
NO | [5 empty] | MANUAL |  |  | 1 | Christmas Holidays | 10 | 10 |  | 2023-12-25 | 2024-01-05 | [9 empty] | 800 | 0
| 20% |  | NO | MIL | mil | NO |  |  | 1 | Key Milestones | 276 | 244 |  | 2023-09-18 | 2024-10-07 | 2023-09-18 | 2024-09-20 | [8 empty] | 0
12 - Down Arrow | 60% |  |  |  | mil |  |  | M001 | 1 | Construction Start |  |  |  | 2023-09-18 |  | 2023-09-18 |  | 2023-09-18 | [7 empty] | 0
| 60% |  | 2R |  | mil |  |  | M002 | 1 | Civil Works Completed |  |  |  |  | 2023-12-22 |  | 2023-12-22 |  |  |  |  | A003 FF | 206 |  |  | 0
| 60% |  | 1M |  | mil |  |  | M003 | 1 | Main Structure Completed |  |  |  |  | 2024-03-15 |  | 2024-03-15 |  |  |  |  | A006 FF | 146 |  |  | 0
| 60% |  | 2M |  | mil |  |  | M004 | 1 | Installations Completed |  |  |  |  | 2024-08-19 |  | 2024-08-02 |  |  |  |  | A013 FF, A014 FF, A015 FF | 35 |  |  | 0
| 60% |  |  |  | mil |  |  | M005 | 1 | Furnishing Completed |  |  |  |  | 2024-09-09 |  | 2024-08-23 |  |  |  |  | A020 FF | 20 |  |  | 0
12 - Down Arrow | 60% |  | 0R |  | mil |  |  | M006 | 1 | Final Acceptance |  |  |  |  | 2024-10-07 |  | 2024-09-20 |  |  |  |  | A023 FF | 0 |  |  | 0
8 | [7 empty] | WBS-1.1 | 1.1 | Foundations | 70 | 70 |  | 2023-09-18 | 2023-12-22 | 2023-09-18 | 2023-12-22 | 2023-09-18 | 2023-10-16 |  |  |  | 0 | 0.26154 | 5200 | 4400
[8 empty] | A001 | 1.1 | Excavation | 20 | 0 | 20 | 2023-09-18 | 2023-10-13 | 2023-09-18 | 2023-10-13 | 2023-09-18 | 2023-10-13 |  |  |  |  | 90% | 800 | 0
[8 empty] | A002 | 1.1 | Concrete Pouring | 40 | 28 | 12 | 2023-10-16 | 2023-12-08 | 2023-10-16 | 2023-12-08 | 2023-10-16 |  |  |  |  | 0 | 20% | 3200 | 3200
[8 empty] | A003 | 1.1 | Backfilling | 30 | 30 |  | 2023-11-13 | 2023-12-22 | 2023-11-13 | 2023-12-22 |  |  |  |  | A002 SS20 | 0 |  | 1200 | 1200
8 | [7 empty] | WBS-1.2 | 1.2 | Structure | 116 | 116 |  | 2023-12-25 | 2024-06-03 | 2023-12-25 | 2024-05-17 | [5 empty] | 0 |  | 17600 | 17600
8 | [7 empty] | WBS-1.2.1 | 1.2.1 | Concrete Works | 61 | 61 |  | 2023-12-25 | 2024-03-18 | 2023-12-25 | 2024-03-15 | [5 empty] | 0 |  | 8000 | 8000
[8 empty] | A004 | 1.2.1 | Concrete Structure | 40 | 40 |  | 2023-12-25 | 2024-02-16 | 2023-12-25 | 2024-02-16 |  |  |  |  | A003 FS | 0 |  | 4800 | 4800
[8 empty] | A005 | 1.2.1 | Floor Slabs | 41 | 41 |  | 2024-01-22 | 2024-03-18 | 2024-01-22 | 2024-03-01 |  |  |  |  | A004 SS20 | 0 |  | 2400 | 2400
[8 empty] | A006 | 1.2.1 | Roof Structure | 20 | 20 |  | 2024-02-19 | 2024-03-15 | 2024-02-19 | 2024-03-15 |  |  |  |  | A004 FS | 131 |  | 800 | 800
8 | [7 empty] | WBS-1.2.2 | 1.2.2 | Walls Erection | 55 | 55 |  | 2024-03-19 | 2024-06-03 | 2024-03-04 | 2024-05-17 | [5 empty] | 0 |  | 9000 | 9000
[8 empty] | A007 | 1.2.2 | Walls Erection | 30 | 30 |  | 2024-03-19 | 2024-04-29 | 2024-03-04 | 2024-04-12 |  |  |  |  | A005 FS | 0 |  | 3600 | 3600
[8 empty] | A008 | 1.2.2 | Insulation | 15 | 15 |  | 2024-04-16 | 2024-05-06 | 2024-04-01 | 2024-04-19 |  |  |  |  | A007 SS20 | 5 |  | 1200 | 1200
[8 empty] | A009 | 1.2.2 | Walls Enclosure | 15 | 15 |  | 2024-04-30 | 2024-05-20 | 2024-04-15 | 2024-05-03 |  |  |  |  | A008 SS10 | 5 |  | 1200 | 1200
[8 empty] | A010 | 1.2.2 | Internal Walls | 25 | 25 |  | 2024-04-30 | 2024-06-03 | 2024-04-15 | 2024-05-17 |  |  |  |  | A007 FS | 15 |  | 3000 | 3000
8 | [7 empty] | WBS-1.2.3 | 1.2.3 | Roof Works | 15 | 15 |  | 2024-04-30 | 2024-05-20 | 2024-04-15 | 2024-05-03 | [5 empty] | 100 |  | 600 | 600
[8 empty] | A011 | 1.2.3 | Roof Waterproofing | 10 | 10 |  | 2024-04-30 | 2024-05-13 | 2024-04-15 | 2024-04-26 |  |  |  |  | A006 FS, A007 FS | 100 |  | 400 | 400
[8 empty] | A012 | 1.2.3 | Roof Painting | 5 | 5 |  | 2024-05-14 | 2024-05-20 | 2024-04-29 | 2024-05-03 |  |  |  |  | A011 FS | 100 |  | 200 | 200
8 | [7 empty] | WBS-1.3 | 1.3 | Installations | 80 | 80 |  | 2024-04-30 | 2024-08-19 | 2024-04-15 | 2024-08-02 | [5 empty] | 0 |  | 9600 | 9600
[8 empty] | A013 | 1.3 | Electrical Installations | 50 | 50 |  | 2024-04-30 | 2024-07-08 | 2024-04-15 | 2024-06-21 |  |  |  |  | A007 FS | 0 |  | 4000 | 4000
[8 empty] | A014 | 1.3 | Plumbing | 50 | 50 |  | 2024-05-21 | 2024-07-29 | 2024-05-06 | 2024-07-12 |  |  |  |  | A013 FF15 | 0 |  | 4000 | 4000
[8 empty] | A015 | 1.3 | HVAC | 40 | 40 |  | 2024-06-25 | 2024-08-19 | 2024-06-10 | 2024-08-02 |  |  |  |  | A014 FF15 | 0 |  | 1600 | 1600
8 | [7 empty] | WBS-1.4 | 1.4 | Furnishing | 75 | 75 |  | 2024-05-28 | 2024-09-09 | 2024-05-13 | 2024-08-23 | [5 empty] | 5 |  | 8400 | 8400
[8 empty] | A016 | 1.4 | Windows | 40 | 40 |  | 2024-05-28 | 2024-07-22 | 2024-05-13 | 2024-07-05 |  |  |  |  | A009 FS5 | 5 |  | 3200 | 3200
[8 empty] | A017 | 1.4 | Doors | 10 | 10 |  | 2024-07-09 | 2024-07-22 | 2024-06-24 | 2024-07-05 |  |  |  |  | A010 FS, A016 FF | 5 |  | 400 | 400
[8 empty] | A018 | 1.4 | Tiling | 25 | 25 |  | 2024-06-04 | 2024-07-08 | 2024-05-20 | 2024-06-21 |  |  |  |  | A010 FS | 15 |  | 2000 | 2000
[8 empty] | A019 | 1.4 | Painting | 30 | 30 |  | 2024-07-23 | 2024-09-02 | 2024-07-08 | 2024-08-16 |  |  |  |  | A016 FS, A017 FS, A018 FS | 5 |  | 2400 | 2400
[8 empty] | A020 | 1.4 | Furniture | 10 | 10 |  | 2024-08-27 | 2024-09-09 | 2024-08-12 | 2024-08-23 |  |  |  |  | A019 FF5 | 5 |  | 400 | 400
8 | [7 empty] | WBS-1.5 | 1.5 | Testing & Delivery | 35 | 35 |  | 2024-08-20 | 2024-10-07 | 2024-08-05 | 2024-09-20 | [5 empty] | 0 |  | 1400 | 1400
[8 empty] | A021 | 1.5 | Installations Testing | 20 | 20 |  | 2024-08-20 | 2024-09-16 | 2024-08-05 | 2024-08-30 |  |  |  |  | A013 FS, A014 FS, A015 FS | 0 |  | 800 | 800
[8 empty] | A022 | 1.5 | Final Touch Ups | 10 | 10 |  | 2024-09-17 | 2024-09-30 | 2024-09-02 | 2024-09-13 |  |  |  |  | A021 FS, A020 FS | 0 |  | 400 | 400
[8 empty] | A023 | 1.5 | Final Walk Through | 5 | 5 |  | 2024-10-01 | 2024-10-07 | 2024-09-16 | 2024-09-20 |  |  |  |  | A022 FS | 0 |  | 200 | 200
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | ACTUAL DURATION | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
[28 empty] | 2023 |  |  |  |  | 2024
Christmas Holidays
Civil Works Completed
Main Structure Completed
Installations Completed
Furnishing Completed
Final Acceptance
Civil Works Completed
Main Structure Completed
Installations Completed
Furnishing Completed
Final Acceptance
Concrete Pouring
Backfilling
Concrete Structure
Floor Slabs
Roof Structure
Walls Erection
Insulation
Walls Enclosure
Internal Walls
Roof Waterproofing
Roof Painting
Electrical Installations
Plumbing
HVAC
Windows
Doors
Tiling
Painting
Furniture
Installations Testing
Final Touch Ups
Final Walk Through
Building Construction
Foundations
Structure
Concrete Works
Walls Erection
Roof Works
Installations
Furnishing
Testing & Delivery

## EPC
[28 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | Month | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
8 | [7 empty] | WBS-1 | 1 | Standard Oil & Gas EPC | 804 | 804 |  | 2025-01-01 | 2028-01-31
| 30% |  |  | MIL | ENG |  |  |  | 1 | ENGINEERING | 368 | 368 |  | 2025-01-01 | 2026-05-31
NO |  |  |  |  | ENG |  |  |  | 1 | Project Kickoff (Engineering begins) | 0 | 0 | 0 | 2025-01-01
|  |  | 1L |  | ENG |  |  |  | 1 | First Submission of P&IDs |  |  | 2 |  | 2025-03-31
|  |  | 2L |  | ENG |  |  |  | 1 | RFIs for Main Equipment Issued |  |  | 4 |  | 2025-05-31
|  |  | 1M |  | ENG |  |  |  | 1 | HAZOP Study |  |  | 6 |  | 2025-07-31
|  |  | 2L |  | ENG |  |  |  | 1 | E&I Load List Approved |  |  | 7 |  | 2025-08-31
|  |  | 2R |  | ENG |  |  |  | 1 | Key Vendor Drawings |  |  | 8 |  | 2025-09-30
|  |  | 1M |  | ENG |  |  |  | 1 | 3D Model 60% |  |  | 9 |  | 2025-10-31
12 - Down Arrow |  |  | 1R |  | ENG |  |  |  | 1 | Foundations IFC |  |  | 10 |  | 2025-11-30
12 - Down Arrow |  |  | 2R |  | ENG |  |  |  | 1 | Isometrics IFC |  |  | 12 |  | 2026-01-31
NO |  |  |  |  | ENG |  |  |  | 1 | Engineering Completed |  |  | 16 |  | 2026-05-31
| 30% |  |  | MIL | PRC |  |  |  | 1 | PROCUREMENT | 522 | 522 |  | 2025-07-31 | 2027-07-31
NO |  |  |  |  | PRC |  |  |  | 1 | Procurement Kickoff (Start of procurement activities) | 0 | 0 | 6 | 2025-07-31
|  |  | 1L |  | PRC |  |  |  | 1 | Long Lead Items Identified |  |  | 8 |  | 2025-09-30
12 - Down Arrow |  |  | 2M |  | PRC |  |  |  | 1 | Purchase Orders (POs) for Main Equipment Placed |  |  | 10 |  | 2025-11-30
|  |  | 1M |  | PRC |  |  |  | 1 | Vendor Kickoff Meetings Held |  |  | 12 |  | 2026-01-31
|  |  | 2M |  | PRC |  |  |  | 1 | First Major Equipment FAT |  |  | 16 |  | 2026-05-31
|  |  | 1M |  | PRC |  |  |  | 1 | Bulk Material Orders Placed |  |  | 18 |  | 2026-07-31
12 - Down Arrow |  |  | 2M |  | PRC |  |  |  | 1 | First Major Equipment Delivered to Site |  |  | 22 |  | 2026-11-30
|  |  | 1M |  | PRC |  |  |  | 1 | Mechanical Equipment On-Site Inspection Completed |  |  | 26 |  | 2027-03-31
NO |  |  |  |  | PRC |  |  |  | 1 | Procurement Close-Out |  |  | 30 |  | 2027-07-31
| 30% |  |  | MIL | CNS |  |  |  | 1 | CONSTRUCTION | 434 | 434 |  | 2026-01-31 | 2027-09-30
|  |  | 1L |  | CNS |  |  |  | 1 | Site Mobilization Completed | 0 | 0 | 12 | 2026-01-31
|  |  | 2L |  | CNS |  |  |  | 1 | First Major Equipment Installed |  |  | 15 |  | 2026-04-30
|  |  | 2M |  | CNS |  |  |  | 1 | Main Steel Structure Erected |  |  | 18 |  | 2026-07-31
12 - Down Arrow |  |  | 1M |  | CNS |  |  |  | 1 | Underground Piping Completed |  |  | 21 |  | 2026-10-31
12 - Down Arrow |  |  | 2M |  | CNS |  |  |  | 1 | Main Process Piping Installed |  |  | 24 |  | 2027-01-31
|  |  | 1M |  | CNS |  |  |  | 1 | Cable Pulling Completed |  |  | 27 |  | 2027-04-30
|  |  | 2R |  | CNS |  |  |  | 1 | Pre-Commissioning Activities Started |  |  | 30 |  | 2027-07-31
[5 empty] | CNS |  |  |  | 1 | Mechanical Completion Certificate (MCC) |  |  | 32 |  | 2027-09-30
| 30% |  |  | MIL | CXX |  |  |  | 1 | COMMISSIONING | 131 | 131 |  | 2027-07-31 | 2028-01-31
|  |  | NO |  | CXX |  |  |  | 1 | Commissioning Kickoff (Start of commissioning) | 0 | 0 | 30 | 2027-07-31
|  |  | 2L |  | CXX |  |  |  | 1 | Pre-Startup Safety Review (PSSR) Completed |  |  | 31 |  | 2027-08-31
12 - Down Arrow |  |  | 1L |  | CXX |  |  |  | 1 | Cold Commissioning Completed |  |  | 32 |  | 2027-09-30
|  |  | 2M |  | CXX |  |  |  | 1 | Hot Commissioning Started |  |  | 33 |  | 2027-10-31
12 - Down Arrow |  |  | 1M |  | CXX |  |  |  | 1 | First Oil/Gas |  |  | 34 |  | 2027-11-30
|  |  | 2R |  | CXX |  |  |  | 1 | Performance Testing Completed |  |  | 35 |  | 2027-12-31
14 - 5 Points Star |  |  | 1R |  | CXX |  |  |  | 1 | Final Handover to Operations Team |  |  | 36 |  | 2028-01-31
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | Month | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
[28 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
First Oil/Gas
First Submission of P&IDs
RFIs for Main Equipment Issued
HAZOP Study
E&I Load List Approved
Key Vendor Drawings
3D Model 60%
Foundations IFC
Isometrics IFC
ENGINEERING
Project Kickoff (Engineering begins)
First Submission of P&IDs
RFIs for Main Equipment Issued
HAZOP Study
E&I Load List Approved
Key Vendor Drawings
3D Model 60%
Foundations IFC
Isometrics IFC
Engineering Completed
Long Lead Items Identified
Purchase Orders (POs) for Main Equipment Placed
Vendor Kickoff Meetings Held
First Major Equipment FAT
Bulk Material Orders Placed
First Major Equipment Delivered to Site
Mechanical Equipment On-Site Inspection Completed
PROCUREMENT
Procurement Kickoff (Start of procurement activities)
Long Lead Items Identified
Purchase Orders (POs) for Main Equipment Placed
Vendor Kickoff Meetings Held
First Major Equipment FAT
Bulk Material Orders Placed
First Major Equipment Delivered to Site
Mechanical Equipment On-Site Inspection Completed
Procurement Close-Out
Site Mobilization Completed
First Major Equipment Installed
Main Steel Structure Erected
Underground Piping Completed
Main Process Piping Installed
Cable Pulling Completed
Pre-Commissioning Activities Started
Mechanical Completion Certificate (MCC)
CONSTRUCTION
Site Mobilization Completed
First Major Equipment Installed
Main Steel Structure Erected
Underground Piping Completed
Main Process Piping Installed
Cable Pulling Completed
Pre-Commissioning Activities Started
Mechanical Completion Certificate (MCC)
Pre-Startup Safety Review (PSSR) Completed
Cold Commissioning Completed
Hot Commissioning Started
First Oil/Gas
Performance Testing Completed
Final Handover to Operations Team
Pre-Startup Safety Review (PSSR) Completed
Cold Commissioning Completed
Hot Commissioning Started
First Oil/Gas
Performance Testing Completed
Final Handover to Operations Team
Standard Oil & Gas EPC

## IT
2025
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
WINDOW | [9 empty] | Summer Holidays | 10 | 10 | 2025-08-11 | 2025-08-22
8 - Summary | [7 empty] | WBS-1 | 1 | IT Project Schedule | 160 | 160 | 2025-03-03 | 2025-10-10
8 | [7 empty] | WBS-1.1 | 1.1 | Initiation | 15 | 15 | 2025-03-03 | 2025-03-21
12 - Down Arrow | [8 empty] | 1.1 | Project Start |  |  | 2025-03-03
[9 empty] | 1.1 | Project Initiation | 5 | 5 | 2025-03-03 | 2025-03-07
[9 empty] | 1.1 | Requirements Gathering | 10 | 10 | 2025-03-10 | 2025-03-21
| 60% | [7 empty] | 1.1 | Requirements Completed |  |  |  | 2025-03-21
8 | [7 empty] | WBS-1.2 | 1.2 | Design | 30 | 30 | 2025-03-24 | 2025-05-02
[9 empty] | 1.2 | System Design | 10 | 10 | 2025-03-24 | 2025-04-04
[9 empty] | 1.2 | Architecture Design | 10 | 10 | 2025-04-07 | 2025-04-18
[9 empty] | 1.2 | Database Design | 10 | 10 | 2025-04-21 | 2025-05-02
| 60% | [7 empty] | 1.2 | Design Completed |  |  |  | 2025-05-02
8 | [7 empty] | WBS-1.3 | 1.3 | Development | 50 | 50 | 2025-05-05 | 2025-07-11
6 - Checkerboard | [8 empty] | 1.3 | Development Phase 1 | 20 | 20 | 2025-05-05 | 2025-05-30
6 - Checkerboard | [8 empty] | 1.3 | Development Phase 2 | 20 | 20 | 2025-06-02 | 2025-06-27
[9 empty] | 1.3 | Integration | 10 | 10 | 2025-06-30 | 2025-07-11
| 60% | [7 empty] | 1.3 | Development Completed |  |  |  | 2025-07-11
8 | [7 empty] | WBS-1.4 | 1.4 | Testing | 50 | 50 | 2025-07-14 | 2025-09-19
[9 empty] | 1.4 | Testing Phase 1 | 10 | 10 | 2025-07-14 | 2025-07-25
[9 empty] | 1.4 | Testing Phase 2 | 10 | 10 | 2025-07-28 | 2025-08-08
3 - Diagonal | 60% | [7 empty] | 1.4 | User Acceptance Testing (UAT) | 10 | 10 | 2025-08-25 | 2025-09-05
[9 empty] | 1.4 | Bug Fixing | 10 | 10 | 2025-09-08 | 2025-09-19
| 60% | [7 empty] | 1.4 | Testing Completed |  |  |  | 2025-09-19
8 | [7 empty] | WBS-1.5 | 1.5 | Deployment | 15 | 15 | 2025-09-22 | 2025-10-10
[9 empty] | 1.5 | Final Review | 5 | 5 | 2025-09-22 | 2025-09-26
3 - Diagonal | 60% | [7 empty] | 1.5 | Deployment | 5 | 5 | 2025-09-29 | 2025-10-03
[9 empty] | 1.5 | Project Closure | 5 | 5 | 2025-10-06 | 2025-10-10
14 - 5 Points Star | 60% | [7 empty] | 1.5 | Project Completed |  |  |  | 2025-10-10
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
2025
Formulas:
START DATE = [START DATE, row below]
FINISH DATE = [FINISH DATE, row above]
Initiation
Project Start
Project Initiation
Requirements Gathering
Requirements Completed
Design
System Design
Architecture Design
Database Design
Design Completed
Development
Development Phase 1
Development Phase 2
Integration
Development Completed
Testing
Testing Phase 1
Testing Phase 2
User Acceptance Testing (UAT)
Bug Fixing
Testing Completed
Deployment
Final Review
Deployment
Project Closure
Project Completed
Summer Holidays
IT Project Schedule

## Consultancy
2024
[28 empty] | Apr |  |  |  |  | May |  |  |  |  | Jun
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | Original Duration | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | 1 | 8 | 15 | 22 | 29 |  | 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24
8 | [7 empty] | WBS-1 | 1 | Consultancy Project Schedule | 60 | 55 |  | 2024-04-01 | 2024-06-21
8 | [7 empty] | WBS-1.1 | 1.1 | Phase 1: Project Initiation | 9 | 4 |  | 2024-04-01 | 2024-04-11
[9 empty] | 1.1 | Project Kickoff Meeting (Align objectives, scope, and stakeholders) | 2 | 0 | 2 | 2024-04-01 | 2024-04-02
[9 empty] | 1.1 | Stakeholder Interviews & Data Collection | 4 | 1 | 4 | 2024-04-03 | 2024-04-08
[9 empty] | 1.1 | Current State Analysis & Preliminary Findings | 3 | 3 | 3 | 2024-04-09 | 2024-04-11
8 | [7 empty] | WBS-1.2 | 1.2 | Phase 2: Research & Analysis | 19 | 19 |  | 2024-04-12 | 2024-05-08
[9 empty] | 1.2 | Benchmarking & Industry Best Practices Review | 4 | 4 | 4 | 2024-04-12 | 2024-04-17
[9 empty] | 1.2 | Gap Analysis & Key Issues Identification | 5 | 5 | 5 | 2024-04-18 | 2024-04-24
[9 empty] | 1.2 | SWOT Analysis & Risk Assessment | 5 | 5 | 5 | 2024-04-25 | 2024-05-01
[9 empty] | 1.2 | Preliminary Recommendations Development | 5 | 5 | 5 | 2024-05-02 | 2024-05-08
8 | [7 empty] | WBS-1.3 | 1.3 | Phase 3: Strategy & Solution Design | 15 | 15 |  | 2024-05-09 | 2024-05-29
[9 empty] | 1.3 | Workshop with Stakeholders to Validate Findings | 5 | 5 | 5 | 2024-05-09 | 2024-05-15
[9 empty] | 1.3 | Development of Strategic Roadmap & Implementation Plan | 5 | 5 | 5 | 2024-05-16 | 2024-05-22
[9 empty] | 1.3 | Financial & Operational Impact Assessment | 5 | 5 | 5 | 2024-05-23 | 2024-05-29
8 | [7 empty] | WBS-1.4 | 1.4 | Phase 4: Report & Deliverables | 17 | 17 |  | 2024-05-30 | 2024-06-21
[9 empty] | 1.4 | Draft Report Preparation | 5 | 5 | 5 | 2024-05-30 | 2024-06-05
[9 empty] | 1.4 | Client Review & Feedback | 5 | 5 | 5 | 2024-06-06 | 2024-06-12
[9 empty] | 1.4 | Final Report & Recommendations Presentation | 5 | 5 | 5 | 2024-06-13 | 2024-06-19
[9 empty] | 1.4 | Project Closure & Lessons Learned Session | 2 | 2 | 2 | 2024-06-20 | 2024-06-21
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | Original Duration | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | 1 | 8 | 15 | 22 | 29 |  | 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24
[28 empty] | Apr |  |  |  |  | May |  |  |  |  | Jun
2024

## Data Center
[27 empty] | 2025 |  | 2026 |  |  |  | 2027
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
8 - Summary | [7 empty] | WBS-1 | 1 | Data Center Construction Schedule | 511 | 511 | 2025-10-01 | 2027-09-15 | [7 empty] | 0
8 - Summary | 40% | [6 empty] | WBS-1.1 | 1.1 | Project Initiation & Planning | 62 | 62 | 2025-10-01 | 2025-12-25 | [7 empty] | 0
[8 empty] | A0010 | 1.1 | Project Kickoff | 10 | 10 | 2025-10-01 | 2025-10-14 | [7 empty] | 0
[8 empty] | A0020 | 1.1 | Permitting & Regulatory Approvals | 52 | 52 | 2025-10-15 | 2025-12-25 | [6 empty] | A0010 FS | 72
8 | 40% | [6 empty] | WBS-1.2 | 1.2 | Engineering & Design | 152 | 152 | 2025-10-15 | 2026-05-14 | [7 empty] | 0
[8 empty] | A0030 | 1.2 | Conceptual & Preliminary Design | 42 | 42 | 2025-10-15 | 2025-12-11 | [6 empty] | A0010 FS | 0
[8 empty] | A0040 | 1.2 | Final Design & Drawings | 80 | 80 | 2025-12-12 | 2026-04-02 | [6 empty] | A0030 FS | 2
[8 empty] | A0050 | 1.2 | Issuance of Construction Drawings | 30 | 30 | 2026-04-03 | 2026-05-14 | [6 empty] | A0040 FS, A0020 FS | 2
8 | 40% | [6 empty] | WBS-1.3 | 1.3 | Procurement | 182 | 182 | 2025-12-12 | 2026-08-24 | [7 empty] | 0
[8 empty] | A0060 | 1.3 | Long Lead Equipment Identification | 20 | 20 | 2025-12-12 | 2026-01-08 | [6 empty] | A0030 FS | 0
[8 empty] | A0070 | 1.3 | Purchase Orders for Electrical & Cooling Equipment | 60 | 60 | 2026-01-09 | 2026-04-02 | [6 empty] | A0060 FS | 0
[8 empty] | A0080 | 1.3 | Orders for Structural & Civil Materials | 30 | 30 | 2026-04-03 | 2026-05-14 | [6 empty] | A0070 FS | 0
[8 empty] | A0090 | 1.3 | Equipment Factory Acceptance Testing (FAT) | 72 | 72 | 2026-05-15 | 2026-08-24 | [6 empty] | A0080 FS | 0
8 | 40% | [6 empty] | WBS-1.4 | 1.4 | Site Preparation & Civil Works | 150 | 150 | 2026-05-15 | 2026-12-10 | [7 empty] | 2
[8 empty] | A0100 | 1.4 | Site Mobilization & Earthworks | 30 | 30 | 2026-05-15 | 2026-06-25 | [6 empty] | A0080 FS, A0050 FS | 2
[8 empty] | A0110 | 1.4 | Foundation & Underground Utilities | 40 | 40 | 2026-06-26 | 2026-08-20 | [6 empty] | A0100 FS | 2
[8 empty] | A0120 | 1.4 | Structural Steel & Enclosure | 80 | 80 | 2026-08-21 | 2026-12-10 | [6 empty] | A0110 FS | 2
8 | 40% | [6 empty] | WBS-1.5 | 1.5 | Erection Works | 182 | 182 | 2026-08-25 | 2027-05-05 | [7 empty] | 0
8 | 30% | [6 empty] | WBS-1.5.A | 1.5.A | Electrical & Mechanical | 182 | 182 | 2026-08-25 | 2027-05-05 | [7 empty] | 0
[8 empty] | A0130 | 1.5.A | UPS, Switchgear, & Generators Installation | 80 | 80 | 2026-08-25 | 2026-12-14 | [6 empty] | A0090 FS | 0
[8 empty] | A0140 | 1.5.A | Cooling System Installation (CRAC/Chillers) | 70 | 70 | 2026-12-15 | 2027-03-22 | [6 empty] | A0130 FS, A0120 FS | 0
[8 empty] | A0150 | 1.5.A | Electrical Testing & Commissioning | 32 | 32 | 2027-03-23 | 2027-05-05 | [6 empty] | A0140 FS | 0
8 | 30% | [6 empty] | WBS-1.5.B | 1.5.B | IT Infrastructure & Networking | 162 | 162 | 2026-08-25 | 2027-04-07 | [7 empty] | 20
[8 empty] | A0160 | 1.5.B | Rack & Cabling Installation | 80 | 80 | 2026-08-25 | 2026-12-14 | [6 empty] | A0090 FS | 20
[8 empty] | A0170 | 1.5.B | Network Equipment & Servers Setup | 60 | 60 | 2026-12-15 | 2027-03-08 | [6 empty] | A0160 FS, A0120 FS | 20
[8 empty] | A0180 | 1.5.B | System Integration Testing | 22 | 22 | 2027-03-09 | 2027-04-07 | [6 empty] | A0170 FS | 20
8 | 40% | [6 empty] | WBS-1.6 | 1.6 | Testing & Commissioning | 70 | 70 | 2027-05-06 | 2027-08-11 | [7 empty] | 0
[8 empty] | A0190 | 1.6 | Full System Testing & Load Simulation | 40 | 40 | 2027-05-06 | 2027-06-30 | [6 empty] | A0150 FS, A0180 FS | 0
[8 empty] | A0200 | 1.6 | Final Uptime & Redundancy Validation | 20 | 20 | 2027-07-01 | 2027-07-28 | [6 empty] | A0190 FS | 0
[8 empty] | A0210 | 1.6 | Handover & Client Acceptance | 10 | 10 | 2027-07-29 | 2027-08-11 | [6 empty] | A0200 FS | 0
8 | 40% | [6 empty] | WBS-1.7 | 1.7 | Project Completion | 25 | 25 | 2027-08-12 | 2027-09-15 | [7 empty] | 0
[8 empty] | A0220 | 1.7 | Documentation & Training | 15 | 15 | 2027-08-12 | 2027-09-01 | [6 empty] | A0210 FS | 0
[8 empty] | A0230 | 1.7 | Final Sign-Off & Project Closure | 10 | 10 | 2027-09-02 | 2027-09-15 | [6 empty] | A0220 FS | 0
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
[27 empty] | 2025 |  | 2026 |  |  |  | 2027
Project Kickoff
Permitting & Regulatory Approvals
Conceptual & Preliminary Design
Final Design & Drawings
Issuance of Construction Drawings
Long Lead Equipment Identification
Purchase Orders for Electrical & Cooling Equipment
Orders for Structural & Civil Materials
Equipment Factory Acceptance Testing (FAT)
Site Mobilization & Earthworks
Foundation & Underground Utilities
Structural Steel & Enclosure
UPS, Switchgear, & Generators Installation
Cooling System Installation (CRAC/Chillers)
Electrical Testing & Commissioning
Rack & Cabling Installation
Network Equipment & Servers Setup
System Integration Testing
Full System Testing & Load Simulation
Final Uptime & Redundancy Validation
Handover & Client Acceptance
Documentation & Training
Final Sign-Off & Project Closure
Project Initiation & Planning
Engineering & Design
Procurement
Site Preparation & Civil Works
Erection Works
Electrical & Mechanical
IT Infrastructure & Networking
Testing & Commissioning
Project Completion
Data Center Construction Schedule

## Railway (Free)
[27 empty] | 2023 |  |  |  | 2024 |  |  |  | 2025
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
12 - Down Arrow | [9 empty] | Railway Project Start |  |  | 2023-03-01
[8 empty] | A0010 | 1.1 | Project Kickoff & Mobilization | 10 | 10 | 2023-03-01 | 2023-03-14 | [7 empty] | 157
[8 empty] | A0020 | 1.1 | Detailed Design & Permits Approvals | 61 | 61 | 2023-03-15 | 2023-06-07 | [7 empty] | 106
[8 empty] | A0025 | 1.2 | TBM Assembly & Shaft Preparation | 40 | 40 | 2023-06-08 | 2023-08-02 | [7 empty] | 127
3 - Diagonal | [7 empty] | A0030 | 1.2 | Tunnel Excavation | 167 | 167 | 2023-08-03 | 2024-03-22 | [7 empty] | 0
[8 empty] | A0035 | 1.2 | Tunnel Lining & Waterproofing | 50 | 50 | 2024-03-25 | 2024-05-31 | [7 empty] | 117
[8 empty] | A0040 | 1.2 | Tunnel Equipment Install (Ventilation, Drainage) | 40 | 40 | 2024-06-03 | 2024-07-26 | [7 empty] | 127
[8 empty] | A0045 | 1.3 | Earthworks & Embankments | 120 | 120 | 2023-06-08 | 2023-11-22 | [7 empty] | 85
3 - Diagonal | [7 empty] | A0050 | 1.3 | Structures (Bridges, Overpasses) | 160 | 160 | 2023-06-22 | 2024-01-31 | [7 empty] | 66
[8 empty] | A0055 | 1.3 | Track Bed Construction | 60 | 60 | 2023-11-23 | 2024-02-14 | [7 empty] | 107
[8 empty] | A0060 | 1.3 | Drainage & Protection Systems | 60 | 60 | 2024-02-15 | 2024-05-08 | [7 empty] | 124
[8 empty] | A0065 | 1.4 | Stations Civil Works | 140 | 140 | 2023-07-06 | 2024-01-17 | [7 empty] | 87
[8 empty] | A0070 | 1.4 | Station MEP + Finishes | 80 | 80 | 2024-01-18 | 2024-05-08 | [7 empty] | 106
[8 empty] | A0080 | 1.5 | Track Install | 107 | 107 | 2024-05-09 | 2024-10-04 | [7 empty] | 135
[8 empty] | A0090 | 1.5 | Electrical Supply & OCS | 170 | 170 | 2024-04-22 | 2024-12-13 | [7 empty] | 114
[8 empty] | A0085 | 1.5 | Signaling & Communication Systems | 90 | 90 | 2024-09-09 | 2025-01-10 | [7 empty] | 126
[8 empty] | A0095 | 1.6 | System Integration & Testing | 29 | 29 | 2025-01-13 | 2025-02-20 | [7 empty] | 138
[8 empty] | A0100 | 1.6 | Trial Operations | 21 | 21 | 2025-02-21 | 2025-03-21 | [7 empty] | 146
[8 empty] | A0105 | 1.6 | Final Handover & Acceptance | 5 | 5 | 2025-03-24 | 2025-03-28 | [7 empty] | 162
[10 empty] | Railway Project Completion |  |  |  | 2025-03-28
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
[27 empty] | 2023 |  |  |  | 2024 |  |  |  | 2025
Formulas:
START DATE = [START DATE, row below]
FINISH DATE = [FINISH DATE, row above]
Drainage & Protection Systems
Station MEP + Finishes
Signaling & Communication Systems
Detailed Design
Tunnel Excavation
Tunnel Equipment Install (Ventilation, Drainage)
Earthworks & Embankments
Track Bed Construction
Drainage & Protection Systems
Stations Civil Works
Station MEP + Finishes
Electrical Supply & OCS
Signaling & Communication Systems
System Integration & Testing
Trial Operations
Final Handover & Acceptance
Project Kickoff & Mobilization
Detailed Design & Permits Approvals
Track Install – Surface Section
Track Install
Tunnel Lining & Waterproofing
Tunnel Equipment Install (Ventilation, Drainage)
TBM Assembly & Shaft Preparation
Structures (Bridges, Overpasses)
Railway Project Start
Railway Project Completion

## Railway (Pro)
[27 empty] | 2023 |  |  |  | 2024 |  |  |  | 2025
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
8 | [7 empty] | WBS-1 | 1 | High-Speed Railway Project Schedule | 562 | 562 | 2023-03-01 | 2025-04-24 | 2023-03-01 | 2025-03-28 | [5 empty] | 0
12 - Down Arrow | 60% | [6 empty] | A0000 | 1 | Project Start |  |  | 2023-03-01 |  | 2023-03-01 | [6 empty] | 0
8 | [7 empty] | WBS-1.1 | 1.1 | Project Management & Design | 120 | 120 | 2023-03-01 | 2023-08-15 | 2023-03-01 | 2023-06-07 | [5 empty] | 0
[8 empty] | A0010 | 1.1 | Project Kickoff & Mobilization | 10 | 10 | 2023-03-01 | 2023-03-14 | 2023-03-01 | 2023-03-14 |  |  |  |  | A0000 SS | 0
[8 empty] | A0015 | 1.1 | Design – Alignment & Tunnel | 40 | 40 | 2023-03-15 | 2023-05-09 | 2023-03-15 | 2023-05-09 |  |  |  |  | A0010 FS | 17
[8 empty] | A0020 | 1.1 | Design – Stations & Surface | 30 | 30 | 2023-05-10 | 2023-06-20 | 2023-03-15 | 2023-05-09 |  |  |  |  | A0015 FS | 17
[8 empty] | A0025 | 1.1 | Design – Electrical Systems & Signaling | 40 | 40 | 2023-06-21 | 2023-08-15 | 2023-03-15 | 2023-05-09 |  |  |  |  | A0020 FS | 197
[8 empty] | A0030 | 1.1 | Environmental Permits & Construction Approvals | 80 | 80 | 2023-03-15 | 2023-07-04 | 2023-03-15 | 2023-06-07 |  |  |  |  | A0010 FS | 0
8 | [7 empty] | WBS-1.2 | 1.2 | Tunnel Works | 297 | 297 | 2023-07-05 | 2024-08-22 | 2023-06-08 | 2024-07-26 | [5 empty] | 0
[8 empty] | A0035 | 1.2 | Shaft Construction & TBM Launch Preparation | 40 | 40 | 2023-07-05 | 2023-08-29 | 2023-06-08 | 2023-08-02 |  |  |  |  | A0030 FS | 0
6 - Checkerboard | [7 empty] | A0040 | 1.2 | Tunnel Excavation (TBM Boring) | 167 | 167 | 2023-08-30 | 2024-04-18 | 2023-08-03 | 2024-03-22 |  |  |  |  | A0035 FS | 0
[8 empty] | A0045 | 1.2 | Secondary Lining & Waterproofing | 50 | 50 | 2024-04-19 | 2024-06-27 | 2024-03-25 | 2024-05-31 |  |  |  |  | A0040 FS | 0
[8 empty] | A0050 | 1.2 | Tunnel Drainage Systems | 20 | 20 | 2024-06-28 | 2024-07-25 | 2024-06-03 | 2024-06-28 |  |  |  |  | A0045 FS | 0
[8 empty] | A0055 | 1.2 | Tunnel Ventilation Systems | 20 | 20 | 2024-07-26 | 2024-08-22 | 2024-07-01 | 2024-07-26 |  |  |  |  | A0050 FS | 0
8 | [7 empty] | WBS-1.3 | 1.3 | Surface Civil Works | 240 | 240 | 2023-07-05 | 2024-06-04 | 2023-06-08 | 2024-05-08 | [5 empty] | 7
[8 empty] | A0060 | 1.3 | Earthworks & Grading | 120 | 120 | 2023-07-05 | 2023-12-19 | 2023-06-08 | 2023-11-22 |  |  |  |  | A0020 FS | 7
[8 empty] | A0065 | 1.3 | Drainage & Slope Protection | 60 | 60 | 2024-03-13 | 2024-06-04 | 2024-02-15 | 2024-05-08 |  |  |  |  | A0080 FS | 7
3 - Diagonal | [7 empty] | A0070 | 1.3 | Bridge Foundations & Piers | 80 | 80 | 2023-09-27 | 2024-01-16 | 2023-06-22 | 2023-10-11 |  |  |  |  | A0060 FF20 | 27
[8 empty] | A0075 | 1.3 | Deck Construction & Superstructure Works | 80 | 80 | 2024-01-17 | 2024-05-07 | 2023-10-12 | 2024-01-31 |  |  |  |  | A0070 FS | 27
[8 empty] | A0080 | 1.3 | Track Bed Construction | 60 | 60 | 2023-12-20 | 2024-03-12 | 2023-11-23 | 2024-02-14 |  |  |  |  | A0060 FS | 7
8 | [7 empty] | WBS-1.4 | 1.4 | Station Construction | 220 | 220 | 2023-08-02 | 2024-06-04 | 2023-07-06 | 2024-05-08 | [5 empty] | 7
[8 empty] | A0085 | 1.4 | Head Station – Civil Works | 140 | 140 | 2023-08-02 | 2024-02-13 | 2023-07-06 | 2024-01-17 |  |  |  |  | A0060 SS20 | 7
[8 empty] | A0090 | 1.4 | Head Station – MEP + Finishing | 80 | 80 | 2024-02-14 | 2024-06-04 | 2024-01-18 | 2024-05-08 |  |  |  |  | A0085 FS | 7
[8 empty] | A0095 | 1.4 | Tail Station – Civil Works | 100 | 100 | 2023-08-02 | 2023-12-19 | 2023-07-06 | 2024-01-17 |  |  |  |  | A0060 SS20 | 57
[8 empty] | A0100 | 1.4 | Tail Station – MEP + Finishing | 70 | 70 | 2023-12-20 | 2024-03-26 | 2024-01-18 | 2024-05-08 |  |  |  |  | A0095 FS | 57
8 | [7 empty] | WBS-1.5 | 1.5 | Track Installation | 107 | 107 | 2024-06-05 | 2024-10-31 | 2024-05-09 | 2024-10-04 | [5 empty] | 0
[8 empty] | A0105 | 1.5 | Ballast & Sleepers – Surface Section | 40 | 40 | 2024-06-05 | 2024-07-30 | 2024-05-09 | 2024-07-03 |  |  |  |  | A0090 FS, A0100 FS, A0075 FS, A0065 FS | 7
[8 empty] | A0110 | 1.5 | Rail Placement – Surface Section | 40 | 40 | 2024-07-31 | 2024-09-24 | 2024-07-04 | 2024-08-28 |  |  |  |  | A0105 FS | 7
[8 empty] | A0115 | 1.5 | Ballast & Sleepers – Tunnel | 25 | 25 | 2024-08-23 | 2024-09-26 | 2024-07-29 | 2024-08-30 |  |  |  |  | A0055 FS | 0
[8 empty] | A0120 | 1.5 | Rail Placement – Tunnel | 25 | 25 | 2024-09-27 | 2024-10-31 | 2024-09-02 | 2024-10-04 |  |  |  |  | A0115 FS | 0
8 | [7 empty] | WBS-1.6 | 1.6 | Electrical & Signaling Systems | 190 | 190 | 2024-05-17 | 2025-02-06 | 2024-04-22 | 2025-01-10 | [5 empty] | 0
[8 empty] | A0125 | 1.6 | Substation Construction & Power Supply Setup | 150 | 150 | 2024-05-17 | 2024-12-12 | 2024-04-22 | 2024-11-15 |  |  |  |  | A0110 FF30, A0120 FF30, A0025 FS | 0
[8 empty] | A0130 | 1.6 | Overhead Catenary System (OCS) Installation | 110 | 110 | 2024-08-09 | 2025-01-09 | 2024-07-15 | 2024-12-13 |  |  |  |  | A0125 FF20, A0110 SS | 0
[8 empty] | A0135 | 1.6 | Signaling & Comms System Installation | 90 | 90 | 2024-10-04 | 2025-02-06 | 2024-09-09 | 2025-01-10 |  |  |  |  | A0130 FF20 | 0
8 | [7 empty] | WBS-1.7 | 1.7 | Testing & Commissioning | 55 | 55 | 2025-02-07 | 2025-04-24 | 2025-01-13 | 2025-03-28 | [5 empty] | 0
[8 empty] | A0140 | 1.7 | Integrated System Testing | 29 | 29 | 2025-02-07 | 2025-03-19 | 2025-01-13 | 2025-02-20 |  |  |  |  | A0135 FS | 0
[8 empty] | A0145 | 1.7 | Trial Runs / Test Trains | 21 | 21 | 2025-03-20 | 2025-04-17 | 2025-02-21 | 2025-03-21 |  |  |  |  | A0140 FS | 0
[8 empty] | A0150 | 1.7 | Final Handover & Acceptance | 5 | 5 | 2025-04-18 | 2025-04-24 | 2025-03-24 | 2025-03-28 |  |  |  |  | A0145 FS | 0
| 60% | [6 empty] | A0160 | 1.7 | Project Completion |  |  |  | 2025-04-24 |  | 2025-03-28 |  |  |  |  | A0150 FF | 0
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
[27 empty] | 2023 |  |  |  | 2024 |  |  |  | 2025

## Railway (Master)-upd
[27 empty] | 2023 |  |  |  | 2024 |  |  |  | 2025
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
8 | [7 empty] | WBS-1 | 1 | High-Speed Railway Project Schedule | 555 | 402 | 2023-03-01 | 2025-04-15 | 2023-03-01 | 2025-03-28 | 2023-03-01 | 2024-04-19 |  |  |  | 0
12 - Down Arrow | 60% | [6 empty] | A0000 | 1 | Project Start |  |  | 2023-03-01 |  | 2023-03-01 |  | 2023-03-01
8 | [7 empty] | WBS-1.1 | 1.1 | Project Management & Design | 120 | 0 | 2023-03-01 | 2023-08-15 | 2023-03-01 | 2023-06-07 | 2023-03-01 | 2023-08-15 |  |  |  | 0
[8 empty] | A0010 | 1.1 | Project Kickoff & Mobilization | 10 | 0 | 2023-03-01 | 2023-03-14 | 2023-03-01 | 2023-03-14 | 2023-03-01 | 2023-03-14 |  |  | A0000 SS |  | 100%
8 | [7 empty] | WBS-1.1.2 | 1.1.2 | Design | 110 | 0 | 2023-03-15 | 2023-08-15 | 2023-03-15 | 2023-05-09 | 2023-03-15 | 2023-08-15
[8 empty] | A0015 | 1.1.2 | Design – Alignment & Tunnel | 40 | 0 | 2023-03-15 | 2023-05-09 | 2023-03-15 | 2023-05-09 | 2023-03-15 | 2023-05-09 |  |  | A0010 FS |  | 100%
[8 empty] | A0020 | 1.1.2 | Design – Stations & Surface | 30 | 0 | 2023-05-10 | 2023-06-20 | 2023-03-15 | 2023-05-09 | 2023-05-10 | 2023-06-20 |  |  | A0015 SS, A0015 FS |  | 100%
[8 empty] | A0025 | 1.1.2 | Design – Electrical Systems & Signaling | 40 | 0 | 2023-06-21 | 2023-08-15 | 2023-03-15 | 2023-05-09 | 2023-06-21 | 2023-08-15 |  |  | A0020 SS, A0020 FS |  | 100%
8 | [7 empty] | WBS-1.1.3 | 1.1.3 | Permits | 80 | 0 | 2023-03-15 | 2023-07-04 | 2023-03-15 | 2023-06-07 | 2023-03-15 | 2023-07-04 |  |  |  | 0
[8 empty] | A0030 | 1.1.3 | Environmental Permits & Construction Approvals | 80 | 0 | 2023-03-15 | 2023-07-04 | 2023-03-15 | 2023-06-07 | 2023-03-15 | 2023-07-04 |  |  | A0010 FS |  | 100%
8 | [7 empty] | WBS-1.2 | 1.2 | Tunnel Works | 275 | 212 | 2023-07-05 | 2024-07-23 | 2023-06-08 | 2024-07-26 | 2023-07-05 | 2024-04-19 |  |  |  | 15
8 | [7 empty] | WBS-1.2.1 | 1.2.1 | Tunnel Construction | 235 | 172 | 2023-07-05 | 2024-05-28 | 2023-06-08 | 2024-05-31 | 2023-07-05 | 2024-04-19 |  |  |  | 15
[8 empty] | A0035 | 1.2.1 | Shaft Construction & TBM Launch Preparation | 40 | 0 | 2023-07-05 | 2023-08-29 | 2023-06-08 | 2023-08-02 | 2023-07-05 | 2023-08-29 |  |  | A0030 FS, A0015 FS |  | 100%
[8 empty] | A0040 | 1.2.1 | Tunnel Excavation (TBM Boring) | 167 | 144 | 2023-08-30 | 2024-04-18 | 2023-08-03 | 2024-03-22 | 2023-08-30 |  |  |  | A0035 FS | 15 | 15%
[8 empty] | A0045 | 1.2.1 | Secondary Lining & Waterproofing | 28 | 28 | 2024-04-19 | 2024-05-28 | 2024-03-25 | 2024-05-31 | 2024-04-19 |  | 2024-04-19 |  | A0040 FS | 15
8 | [7 empty] | WBS-1.2.2 | 1.2.2 | Tunnel Installations | 40 | 40 | 2024-05-29 | 2024-07-23 | 2024-06-03 | 2024-07-26 | [5 empty] | 15
[8 empty] | A0050 | 1.2.2 | Tunnel Drainage Systems | 20 | 20 | 2024-05-29 | 2024-06-25 | 2024-06-03 | 2024-06-28 |  |  |  |  | A0045 FS | 15
[8 empty] | A0055 | 1.2.2 | Tunnel Ventilation Systems | 20 | 20 | 2024-06-26 | 2024-07-23 | 2024-07-01 | 2024-07-26 |  |  |  |  | A0050 FS | 15
8 | [7 empty] | WBS-1.3 | 1.3 | Surface Civil Works | 240 | 177 | 2023-07-05 | 2024-06-04 | 2023-06-08 | 2024-05-08 | 2023-07-05 | 2023-07-05 |  |  |  | 0
8 | [7 empty] | WBS-1.3.1 | 1.3.1 | Earthworks | 240 | 177 | 2023-07-05 | 2024-06-04 | 2023-06-08 | 2024-05-08 | 2023-07-05 | 2023-07-05 |  |  |  | 0
[8 empty] | A0060 | 1.3.1 | Earthworks & Grading | 120 | 57 | 2023-07-05 | 2023-12-19 | 2023-06-08 | 2023-11-22 | 2023-07-05 |  |  |  | A0030 FS, A0020 FS | 0 | 40%
[8 empty] | A0065 | 1.3.1 | Drainage & Slope Protection | 60 | 60 | 2024-03-13 | 2024-06-04 | 2024-02-15 | 2024-05-08 |  |  |  |  | A0080 FS | 0
8 | [7 empty] | WBS-1.3.2 | 1.3.2 | Bridge Erection | 160 | 160 | 2023-10-02 | 2024-05-10 | 2023-06-22 | 2024-01-31 | [5 empty] | 17
[8 empty] | A0070 | 1.3.2 | Bridge Foundations & Piers | 80 | 80 | 2023-10-02 | 2024-01-19 | 2023-06-22 | 2023-10-11 |  |  |  |  | A0060 SS10, A0060 FF20 | 17
[8 empty] | A0075 | 1.3.2 | Deck Construction & Superstructure Works | 80 | 80 | 2024-01-22 | 2024-05-10 | 2023-10-12 | 2024-01-31 |  |  |  |  | A0070 FS | 17
8 | [7 empty] | WBS-1.3.3 | 1.3.3 | Bed Construction | 60 | 60 | 2023-12-20 | 2024-03-12 | 2023-11-23 | 2024-02-14 | [5 empty] | 0
[8 empty] | A0080 | 1.3.3 | Track Bed Construction | 60 | 60 | 2023-12-20 | 2024-03-12 | 2023-11-23 | 2024-02-14 |  |  |  |  | A0060 FS | 0
8 | [7 empty] | WBS-1.4 | 1.4 | Station Construction | 179 | 153 | 2023-08-25 | 2024-05-01 | 2023-07-06 | 2024-05-08 | 2023-08-25 | 2023-09-07 |  |  |  | 24
8 | [7 empty] | WBS-1.4.1 | 1.4.1 | Head Station | 179 | 153 | 2023-08-25 | 2024-05-01 | 2023-07-06 | 2024-05-08 | 2023-08-25 | 2023-08-25 |  |  |  | 24
[8 empty] | A0085 | 1.4.1 | Head Station – Civil Works | 99 | 73 | 2023-08-25 | 2024-01-10 | 2023-07-06 | 2024-01-17 | 2023-08-25 |  |  |  | A0060 SS20, A0020 FS | 24 | 10%
[8 empty] | A0090 | 1.4.1 | Head Station – MEP + Finishing | 80 | 80 | 2024-01-11 | 2024-05-01 | 2024-01-18 | 2024-05-08 |  |  |  |  | A0085 FS | 24
8 | [7 empty] | WBS-1.4.2 | 1.4.2 | Tail Station | 116 | 99 | 2023-09-07 | 2024-02-15 | 2023-07-06 | 2024-05-08 | 2023-09-07 | 2023-09-07 |  |  |  | 78
[8 empty] | A0095 | 1.4.2 | Tail Station – Civil Works | 46 | 29 | 2023-09-07 | 2023-11-09 | 2023-07-06 | 2024-01-17 | 2023-09-07 |  |  |  | A0060 SS20, A0020 FS | 78 | 60%
[8 empty] | A0100 | 1.4.2 | Tail Station – MEP + Finishing | 70 | 70 | 2023-11-10 | 2024-02-15 | 2024-01-18 | 2024-05-08 |  |  |  |  | A0095 FS | 78
8 | [7 empty] | WBS-1.5 | 1.5 | Track Installation | 85 | 85 | 2024-06-05 | 2024-10-01 | 2024-05-09 | 2024-10-04 | [5 empty] | 0
8 | [7 empty] | WBS-1.5.1 | 1.5.1 | Surface | 80 | 80 | 2024-06-05 | 2024-09-24 | 2024-05-09 | 2024-08-28 | [5 empty] | 0
[8 empty] | A0105 | 1.5.1 | Ballast & Sleepers – Surface Section | 40 | 40 | 2024-06-05 | 2024-07-30 | 2024-05-09 | 2024-07-03 |  |  |  |  | A0090 FS, A0100 FS, A0075 FS, A0065 FS | 0
[8 empty] | A0110 | 1.5.1 | Rail Placement – Surface Section | 40 | 40 | 2024-07-31 | 2024-09-24 | 2024-07-04 | 2024-08-28 |  |  |  |  | A0105 FS | 0
8 | [7 empty] | WBS-1.5.2 | 1.5.2 | Tunnel | 50 | 50 | 2024-07-24 | 2024-10-01 | 2024-07-29 | 2024-10-04 | [5 empty] | 15
[8 empty] | A0115 | 1.5.2 | Ballast & Sleepers – Tunnel | 25 | 25 | 2024-07-24 | 2024-08-27 | 2024-07-29 | 2024-08-30 |  |  |  |  | A0055 FS | 15
[8 empty] | A0120 | 1.5.2 | Rail Placement – Tunnel | 25 | 25 | 2024-08-28 | 2024-10-01 | 2024-09-02 | 2024-10-04 |  |  |  |  | A0115 FS | 15
8 | [7 empty] | WBS-1.6 | 1.6 | Electrical & Signaling Systems | 205 | 205 | 2024-04-17 | 2025-01-28 | 2024-04-22 | 2025-01-10 | [5 empty] | 0
[8 empty] | A0125 | 1.6 | Substation Construction & Power Supply Setup | 150 | 150 | 2024-04-17 | 2024-11-12 | 2024-04-22 | 2024-11-15 |  |  |  |  | A0110 FF30, A0120 FF30, A0025 FS | 15
[8 empty] | A0130 | 1.6 | Overhead Catenary System (OCS) Installation | 110 | 110 | 2024-07-31 | 2024-12-31 | 2024-07-15 | 2024-12-13 |  |  |  |  | A0125 FF20, A0110 SS | 0
[8 empty] | A0135 | 1.6 | Signaling & Comms System Installation | 90 | 90 | 2024-09-25 | 2025-01-28 | 2024-09-09 | 2025-01-10 |  |  |  |  | A0130 FF20 | 0
8 | [7 empty] | WBS-1.7 | 1.7 | Testing & Commissioning | 55 | 55 | 2025-01-29 | 2025-04-15 | 2025-01-13 | 2025-03-28 | [5 empty] | 0
[8 empty] | A0140 | 1.7 | Integrated System Testing | 29 | 29 | 2025-01-29 | 2025-03-10 | 2025-01-13 | 2025-02-20 |  |  |  |  | A0130 FS, A0135 FS, A0125 FS | 0
[8 empty] | A0145 | 1.7 | Trial Runs / Test Trains | 21 | 21 | 2025-03-11 | 2025-04-08 | 2025-02-21 | 2025-03-21 |  |  |  |  | A0140 FS | 0
[8 empty] | A0150 | 1.7 | Final Handover & Acceptance | 5 | 5 | 2025-04-09 | 2025-04-15 | 2025-03-24 | 2025-03-28 |  |  |  |  | A0145 FS | 0
| 60% | [6 empty] | A0160 | 1.7 | Project Completion |  |  |  | 2025-04-15 |  | 2025-03-28 |  |  |  |  | A0150 FF | 0
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
[27 empty] | 2023 |  |  |  | 2024 |  |  |  | 2025
15-Apr-25
23-Jul-24
28-May-24
18-Apr-24
28-May-24
19-Apr-24
23-Jul-24
29-May-24
25-Jun-24
29-May-24
23-Jul-24
26-Jun-24
04-Jun-24
04-Jun-24
19-Dec-23
04-Jun-24
13-Mar-24
10-May-24
02-Oct-23
19-Jan-24
02-Oct-23
10-May-24
22-Jan-24
12-Mar-24
20-Dec-23
12-Mar-24
20-Dec-23
01-May-24
01-May-24
10-Jan-24
01-May-24
11-Jan-24
15-Feb-24
09-Nov-23
15-Feb-24
10-Nov-23
01-Oct-24
05-Jun-24
24-Sep-24
05-Jun-24
30-Jul-24
05-Jun-24
24-Sep-24
31-Jul-24
01-Oct-24
24-Jul-24
27-Aug-24
24-Jul-24
01-Oct-24
28-Aug-24
28-Jan-25
17-Apr-24
12-Nov-24
17-Apr-24
31-Dec-24
31-Jul-24
28-Jan-25
25-Sep-24
15-Apr-25
29-Jan-25
10-Mar-25
29-Jan-25
08-Apr-25
11-Mar-25
15-Apr-25
09-Apr-25
15-Apr-25

## Railway (Master)
[27 empty] | 2022 | 2023 |  |  |  | 2024 |  |  |  | 2025
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
8 | [7 empty] | WBS-1 | 1 | High-Speed Railway Project Schedule | 562 | 562 | 2023-03-01 | 2025-04-24 | 2023-03-01 | 2025-03-28 | 2023-03-01 | 2024-08-22 |  |  |  | 0
12 - Down Arrow | 60% | [6 empty] | A0000 | 1 | Project Start |  |  | 2023-03-01 |  | 2023-03-01 |  | 2023-03-01 |  |  |  |  | 0
8 | [7 empty] | WBS-1.1 | 1.1 | Project Management & Design | 120 | 120 | 2023-03-01 | 2023-08-15 | 2023-03-01 | 2023-06-07 | 2023-03-01 | 2023-08-15 |  |  |  | 0
[8 empty] | A0010 | 1.1 | Project Kickoff & Mobilization | 10 | 10 | 2023-03-01 | 2023-03-14 | 2023-03-01 | 2023-03-14 | 2023-03-01 | 2023-03-14 |  |  | A0000 SS | 0
8 | [7 empty] | WBS-1.1.2 | 1.1.2 | Design | 110 | 110 | 2023-03-15 | 2023-08-15 | 2023-03-15 | 2023-05-09 | 2023-03-15 | 2023-08-15 |  |  |  | 17
[8 empty] | A0015 | 1.1.2 | Design – Alignment & Tunnel | 40 | 40 | 2023-03-15 | 2023-05-09 | 2023-03-15 | 2023-05-09 | 2023-03-15 | 2023-05-09 |  |  | A0010 FS | 17
[8 empty] | A0020 | 1.1.2 | Design – Stations & Surface | 30 | 30 | 2023-05-10 | 2023-06-20 | 2023-03-15 | 2023-05-09 | 2023-05-10 | 2023-06-20 |  |  | A0015 SS, A0015 FS | 17
[8 empty] | A0025 | 1.1.2 | Design – Electrical Systems & Signaling | 40 | 40 | 2023-06-21 | 2023-08-15 | 2023-03-15 | 2023-05-09 | 2023-06-21 | 2023-08-15 |  |  | A0020 SS, A0020 FS | 197
8 | [7 empty] | WBS-1.1.3 | 1.1.3 | Permits | 80 | 80 | 2023-03-15 | 2023-07-04 | 2023-03-15 | 2023-06-07 | 2023-03-15 | 2023-07-04 |  |  |  | 0
[8 empty] | A0030 | 1.1.3 | Environmental Permits & Construction Approvals | 80 | 80 | 2023-03-15 | 2023-07-04 | 2023-03-15 | 2023-06-07 | 2023-03-15 | 2023-07-04 |  |  | A0010 FS | 0
8 | [7 empty] | WBS-1.2 | 1.2 | Tunnel Works | 297 | 297 | 2023-07-05 | 2024-08-22 | 2023-06-08 | 2024-07-26 | 2023-07-05 | 2024-08-22 |  |  |  | 0
8 | [7 empty] | WBS-1.2.1 | 1.2.1 | Tunnel Construction | 257 | 257 | 2023-07-05 | 2024-06-27 | 2023-06-08 | 2024-05-31 | 2023-07-05 | 2024-06-27 |  |  |  | 0
[8 empty] | A0035 | 1.2.1 | Shaft Construction & TBM Launch Preparation | 40 | 40 | 2023-07-05 | 2023-08-29 | 2023-06-08 | 2023-08-02 | 2023-07-05 | 2023-08-29 |  |  | A0030 FS, A0015 FS | 0
[8 empty] | A0040 | 1.2.1 | Tunnel Excavation (TBM Boring) | 167 | 167 | 2023-08-30 | 2024-04-18 | 2023-08-03 | 2024-03-22 | 2023-08-30 | 2024-04-18 |  |  | A0035 FS | 0
[8 empty] | A0045 | 1.2.1 | Secondary Lining & Waterproofing | 50 | 50 | 2024-04-19 | 2024-06-27 | 2024-03-25 | 2024-05-31 | 2024-04-19 | 2024-06-27 |  |  | A0040 FS | 0
8 | [7 empty] | WBS-1.2.2 | 1.2.2 | Tunnel Installations | 40 | 40 | 2024-06-28 | 2024-08-22 | 2024-06-03 | 2024-07-26 | 2024-06-28 | 2024-08-22 |  |  |  | 0
[8 empty] | A0050 | 1.2.2 | Tunnel Drainage Systems | 20 | 20 | 2024-06-28 | 2024-07-25 | 2024-06-03 | 2024-06-28 | 2024-06-28 | 2024-07-25 |  |  | A0045 FS | 0
[8 empty] | A0055 | 1.2.2 | Tunnel Ventilation Systems | 20 | 20 | 2024-07-26 | 2024-08-22 | 2024-07-01 | 2024-07-26 | 2024-07-26 | 2024-08-22 |  |  | A0050 FS | 0
8 | [7 empty] | WBS-1.3 | 1.3 | Surface Civil Works | 240 | 240 | 2023-07-05 | 2024-06-04 | 2023-06-08 | 2024-05-08 | 2023-07-05 | 2023-12-19 |  |  |  | 7
8 | [7 empty] | WBS-1.3.1 | 1.3.1 | Earthworks | 240 | 240 | 2023-07-05 | 2024-06-04 | 2023-06-08 | 2024-05-08 | 2023-07-05 | 2023-12-19 |  |  |  | 7
[8 empty] | A0060 | 1.3.1 | Earthworks & Grading | 120 | 120 | 2023-07-05 | 2023-12-19 | 2023-06-08 | 2023-11-22 | 2023-07-05 | 2023-12-19 |  |  | A0030 FS, A0020 FS | 7
[8 empty] | A0065 | 1.3.1 | Drainage & Slope Protection | 60 | 60 | 2024-03-13 | 2024-06-04 | 2024-02-15 | 2024-05-08 |  |  |  |  | A0080 FS | 7
8 | [7 empty] | WBS-1.3.2 | 1.3.2 | Bridge Erection | 160 | 160 | 2023-09-27 | 2024-05-07 | 2023-06-22 | 2024-01-31 | [5 empty] | 27
[8 empty] | A0070 | 1.3.2 | Bridge Foundations & Piers | 80 | 80 | 2023-09-27 | 2024-01-16 | 2023-06-22 | 2023-10-11 |  |  |  |  | A0060 SS10, A0060 FF20 | 27
[8 empty] | A0075 | 1.3.2 | Deck Construction & Superstructure Works | 80 | 80 | 2024-01-17 | 2024-05-07 | 2023-10-12 | 2024-01-31 |  |  |  |  | A0070 FS | 27
8 | [7 empty] | WBS-1.3.3 | 1.3.3 | Bed Construction | 60 | 60 | 2023-12-20 | 2024-03-12 | 2023-11-23 | 2024-02-14 | [5 empty] | 7
[8 empty] | A0080 | 1.3.3 | Track Bed Construction | 60 | 60 | 2023-12-20 | 2024-03-12 | 2023-11-23 | 2024-02-14 |  |  |  |  | A0060 FS | 7
8 | [7 empty] | WBS-1.4 | 1.4 | Station Construction | 220 | 220 | 2023-08-02 | 2024-06-04 | 2023-07-06 | 2024-05-08 | [5 empty] | 7
8 | [7 empty] | WBS-1.4.1 | 1.4.1 | Head Station | 220 | 220 | 2023-08-02 | 2024-06-04 | 2023-07-06 | 2024-05-08 | [5 empty] | 7
[8 empty] | A0085 | 1.4.1 | Head Station – Civil Works | 140 | 140 | 2023-08-02 | 2024-02-13 | 2023-07-06 | 2024-01-17 |  |  |  |  | A0060 SS20, A0020 FS | 7
[8 empty] | A0090 | 1.4.1 | Head Station – MEP + Finishing | 80 | 80 | 2024-02-14 | 2024-06-04 | 2024-01-18 | 2024-05-08 |  |  |  |  | A0085 FS | 7
8 | [7 empty] | WBS-1.4.2 | 1.4.2 | Tail Station | 170 | 170 | 2023-08-02 | 2024-03-26 | 2023-07-06 | 2024-05-08 | [5 empty] | 57
[8 empty] | A0095 | 1.4.2 | Tail Station – Civil Works | 100 | 100 | 2023-08-02 | 2023-12-19 | 2023-07-06 | 2024-01-17 |  |  |  |  | A0060 SS20, A0020 FS | 57
[8 empty] | A0100 | 1.4.2 | Tail Station – MEP + Finishing | 70 | 70 | 2023-12-20 | 2024-03-26 | 2024-01-18 | 2024-05-08 |  |  |  |  | A0095 FS | 57
8 | [7 empty] | WBS-1.5 | 1.5 | Track Installation | 107 | 107 | 2024-06-05 | 2024-10-31 | 2024-05-09 | 2024-10-04 | [5 empty] | 0
8 | [7 empty] | WBS-1.5.1 | 1.5.1 | Surface | 80 | 80 | 2024-06-05 | 2024-09-24 | 2024-05-09 | 2024-08-28 | [5 empty] | 7
[8 empty] | A0105 | 1.5.1 | Ballast & Sleepers – Surface Section | 40 | 40 | 2024-06-05 | 2024-07-30 | 2024-05-09 | 2024-07-03 |  |  |  |  | A0090 FS, A0100 FS, A0075 FS, A0065 FS | 7
[8 empty] | A0110 | 1.5.1 | Rail Placement – Surface Section | 40 | 40 | 2024-07-31 | 2024-09-24 | 2024-07-04 | 2024-08-28 |  |  |  |  | A0105 FS | 7
8 | [7 empty] | WBS-1.5.2 | 1.5.2 | Tunnel | 50 | 50 | 2024-08-23 | 2024-10-31 | 2024-07-29 | 2024-10-04 | [5 empty] | 0
[8 empty] | A0115 | 1.5.2 | Ballast & Sleepers – Tunnel | 25 | 25 | 2024-08-23 | 2024-09-26 | 2024-07-29 | 2024-08-30 |  |  |  |  | A0055 FS | 0
[8 empty] | A0120 | 1.5.2 | Rail Placement – Tunnel | 25 | 25 | 2024-09-27 | 2024-10-31 | 2024-09-02 | 2024-10-04 |  |  |  |  | A0115 FS | 0
8 | [7 empty] | WBS-1.6 | 1.6 | Electrical & Signaling Systems | 190 | 190 | 2024-05-17 | 2025-02-06 | 2024-04-22 | 2025-01-10 | [5 empty] | 0
[8 empty] | A0125 | 1.6 | Substation Construction & Power Supply Setup | 150 | 150 | 2024-05-17 | 2024-12-12 | 2024-04-22 | 2024-11-15 |  |  |  |  | A0110 FF30, A0120 FF30, A0025 FS | 0
[8 empty] | A0130 | 1.6 | Overhead Catenary System (OCS) Installation | 110 | 110 | 2024-08-09 | 2025-01-09 | 2024-07-15 | 2024-12-13 |  |  |  |  | A0125 FF20, A0110 SS | 0
[8 empty] | A0135 | 1.6 | Signaling & Comms System Installation | 90 | 90 | 2024-10-04 | 2025-02-06 | 2024-09-09 | 2025-01-10 |  |  |  |  | A0130 FF20 | 0
8 | [7 empty] | WBS-1.7 | 1.7 | Testing & Commissioning | 55 | 55 | 2025-02-07 | 2025-04-24 | 2025-01-13 | 2025-03-28 | [5 empty] | 0
[8 empty] | A0140 | 1.7 | Integrated System Testing | 29 | 29 | 2025-02-07 | 2025-03-19 | 2025-01-13 | 2025-02-20 |  |  |  |  | A0130 FS, A0135 FS, A0125 FS | 0
[8 empty] | A0145 | 1.7 | Trial Runs / Test Trains | 21 | 21 | 2025-03-20 | 2025-04-17 | 2025-02-21 | 2025-03-21 |  |  |  |  | A0140 FS | 0
[8 empty] | A0150 | 1.7 | Final Handover & Acceptance | 5 | 5 | 2025-04-18 | 2025-04-24 | 2025-03-24 | 2025-03-28 |  |  |  |  | A0145 FS | 0
| 60% | [6 empty] | A0160 | 1.7 | Project Completion |  |  |  | 2025-04-24 |  | 2025-03-28 |  |  |  |  | A0150 FF | 0
act / mil style | shape height | connect style | label pos | timeline mode | timeline code | schedule mode | units distrib. curve | ACTIVITY ID | WBS | DESCRIPTION | TOTAL DURATION | REMAINING DURATION | START DATE | FINISH DATE | BL START DATE | BL FINISH DATE | ACTUAL START DATE | ACTUAL FINISH DATE | RESUME DATE | CONSTRAINT DATE | PREDECESSORS | FLOAT | PROGRESS % | BUDGET UNITS | REMAINING UNITS | Period | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
[27 empty] | 2022 | 2023 |  |  |  | 2024 |  |  |  | 2025
04-Jun-24
13-Mar-24
07-May-24
27-Sep-23
16-Jan-24
27-Sep-23
07-May-24
17-Jan-24
12-Mar-24
20-Dec-23
12-Mar-24
20-Dec-23
04-Jun-24
02-Aug-23
04-Jun-24
02-Aug-23
13-Feb-24
02-Aug-23
04-Jun-24
14-Feb-24
26-Mar-24
02-Aug-23
19-Dec-23
02-Aug-23
26-Mar-24
20-Dec-23
31-Oct-24
05-Jun-24
24-Sep-24
05-Jun-24
30-Jul-24
05-Jun-24
24-Sep-24
31-Jul-24
31-Oct-24
23-Aug-24
26-Sep-24
23-Aug-24
31-Oct-24
27-Sep-24
06-Feb-25
17-May-24
12-Dec-24
17-May-24
09-Jan-25
09-Aug-24
06-Feb-25
04-Oct-24
24-Apr-25
07-Feb-25
19-Mar-25
07-Feb-25
17-Apr-25
20-Mar-25
24-Apr-25
18-Apr-25
24-Apr-25
24-Apr-25
01-Mar-23
01-Mar-23
15-Aug-23
01-Mar-23
14-Mar-23
01-Mar-23
15-Aug-23
15-Mar-23
09-May-23
15-Mar-23
20-Jun-23
10-May-23
15-Aug-23
21-Jun-23
04-Jul-23
15-Mar-23
04-Jul-23
15-Mar-23
22-Aug-24
05-Jul-23
27-Jun-24
05-Jul-23
29-Aug-23
05-Jul-23
18-Apr-24
30-Aug-23
27-Jun-24
19-Apr-24
22-Aug-24
28-Jun-24
25-Jul-24
28-Jun-24
22-Aug-24
26-Jul-24
04-Jun-24
05-Jul-23
04-Jun-24
05-Jul-23
19-Dec-23
05-Jul-23

## Settings Railway (M)
GANTTASIZER SETTINGS
Group WBS | TRUE
Calendar Period | 5
Week Start Day | 0
Period Width | 4
Start Extra Periods | 1
Finsih Extra Periods | 1
Cutoff Date | 2023-02-28
Bar Style | 1
Milestone Style | 0
Shape Height | 3
Label: Description | FALSE
Label: Finish | TRUE
Label: Duration | FALSE
Label: Start | TRUE
Label: Show on Actuals | FALSE
Remaining Bar Color | 3
Actual Bar Color | 5
BL Bar Color | 1
Progress Bar Color | 2
Float Bar Color | 9
Milestone Color | 0
Cutoff Line Color | 6
Relationship Type | 0
Relationship Lag | 0
Connector Style | 0
Connector Thickness | 2
Sunday | FALSE
Monday | TRUE
Tuesday | TRUE
Wednesday | TRUE
Thursday | TRUE
Friday | TRUE
Saturday | FALSE
Units Distribution Curve | 0
Auto Update Chart | TRUE
Auto Distribute Units | FALSE
Auto Update Schedule | FALSE
Auto Update Row Height | TRUE
Update Time Scale with Chart | TRUE
Allow Set Actuals Color | FALSE
Show Base Line | TRUE
Show Progress Bar | FALSE
Show Float Bar | FALSE
Calendar Exceptions